Implementation Plan

(Click Link to Obtain Latest Version of Template V3 – 14/10/26)

SP Exit DEA : MCX LD5 and LD8 to SWI and UXB ACI Interconnect Build – Implementation Plan

Workstream: Foundational Infrastructure (SP Exit)
Change Coordinator/Author: Jonathan Clowes

# Contents

1

1.1	References & Associated Documents	2

1.2	Business Contacts	2

2	Implementation Plan Requirements & Overview	3

2.1	Title Of Change	3

2.2	Description Of Change	3

2.3	Business Justification Of Change	3

2.4	Potential Impact of Change	3

2.5	Change Readiness & Risk Controls	3

2.6	Requirements & Dependencies	4

2.7	Flow Topology / Technical Schematic	4

2.8	Resource requirements	4

3	Implementation Summary	5

3.1	Change Window	5

3.2	Outage Timings (if any)	5

3.3	Execution Summary & Communication Plan	5

4	Detailed Implementation Plan	6

4.1	Pre-Requisites, Testing & Communication	6

4.2	Implementation	7

5	Post Change Validation Testing	8

6	Rollback	10

7	Close Down	11

Document History

| Document Created/Amended By | Date | Reviewed by | Changes | Version |
| --- | --- | --- | --- | --- |
| Jonathan Clowes | 15th Oct. 2026 |  | Initial Draft for approval | 0.1 |
| Jonathan Clowes | 16th Oct. 2026 |  | Added LD5-LD8 interconnects | 1.0 |
| Andrew MacPhail | 22nd Oct 2026 |  | Added Timings and moved to version 3 on template. | 1.1 |

## References & Associated Documents

| Document | Date | Owner |
| --- | --- | --- |
| N/A | N/A | N/A |

## Business Contacts

| Business Owner | Ian Kirk | Business Sponsor | Sal Ahmed |
| --- | --- | --- | --- |

# Implementation Plan Requirements & Overview

## Title Of Change

MCX LD5 and LD8 to SWI and UXB ACI interconnect: build with BGP established and no routes exchanged.

## Description Of Change

Scope: MCX-LD5-EX4650-INNER-01 and MCX-LD8-EX4650-INNER-01 (mcx_vrf), SWI border leafs 1701 and 1702, and UXB border leafs 2703 and 2704 (PROD_TNT / PROD_VRF).  No application traffic is in scope, because no routes are exchanged by this change.

Activity: Build four new links, one Vodafone circuit each, from LD5 and LD8 to the SWI and UXB ACI fabrics.  Each MCX site lands on a different leaf in each fabric, LD5 on 1701 and 2703 and LD8 on 1702 and 2704.  Each link has a VLAN and irb in mcx_vrf on the EX4650 and an SVI on the leaf, with eBGP, BFD and MD5 across it, the ACI access policies for the new leaf ports, and a new MCX_L3OUT on each fabric.  Every BGP session is built with DENY-ALL in both directions on the EX4650s, and with import route control enforced and nothing associated on ACI, so the four sessions to the fabrics come up without any routes being advertised or received.  A fifth link is built between LD5 and LD8, with a VLAN and irb in mcx_vrf on each switch and eBGP between them with DENY-ALL in both directions, so it comes up without any routes being exchanged.

## Business Justification Of Change

Why: This is part of SPExit.  The new links give MCX direct routed connectivity to both ACI fabrics.

Benefit: Building the links and bringing BGP up the circuits, BFD and BGP with no risk to live traffic, and separates the physical build from the future routing change.

Impact of not doing it: The SPExit migration of MCX traffic onto the ACI fabrics cannot go ahead, which delays the decommission of Stockley Park.

## Potential Impact of Change

No service impact is expected.  All interfaces, VLANs, irbs, BGP groups and ACI objects are new, the existing mcx_vrf BGP peers and existing L3Outs are not changed, and no routes are exchanged on the new sessions.

## Change Readiness & Risk Controls

What steps/controls have been put in place, to ensure the successful delivery of this change?

Pre-checks have confirmed the ports, VLANs, irbs and subnets are free on both EX4650s and both fabrics.  All config is pre-written and peer reviewed, a config archive is taken on both EX4650s and a snapshot on both APICs before any change, and the EX4650 changes are applied with commit confirmed.  Likelihood of failure is low.

Has this type of change been successfully implemented previously?

Yes new WAN connections have been configured many times before on SP Exit.

Has the change been fully tested within a Non-Production environment and/or follow an existing SOP?

- We do not have a suitable non production environment in which to test this but have added many new WAN links as part of Sp Exit.

## Requirements & Dependencies

All five Vodafone circuits delivered, with light levels recorded at both ends, and patched as below

| Link | A end device | A end port | A end IP | B end device | B end port | B end IP | VLAN | Vodafone ref |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LD5 to SWI | MCX-LD5-EX4650-INNER-01 | xe-0/0/20 (FPC 0) | 10.158.240.241/29 | SWI-B2D01U37-LEA-1701 | Eth1/40 | 10.158.240.242/29 | 725 |  |
| LD8 to SWI | MCX-LD8-EX4650-INNER-01 | xe-0/0/20 (FPC 0) | 10.158.240.249/29 | SWI-B2D03U44-LEA-1702 | Eth1/40 | 10.158.240.250/29 | 726 |  |
| LD5 to UXB | MCX-LD5-EX4650-INNER-01 | xe-1/0/20 (FPC 1) | 10.157.240.217/29 | UXB leaf 2703 | Eth1/40 | 10.157.240.218/29 | 727 |  |
| LD8 to UXB | MCX-LD8-EX4650-INNER-01 | xe-1/0/20 (FPC 1) | 10.157.240.209/29 | UXB leaf 2704 | Eth1/40 | 10.157.240.210/29 | 728 |  |
| LD5 to LD8 | MCX-LD5-EX4650-INNER-01 | xe-0/0/24 (FPC 0) | TBC | MCX-LD8-EX4650-INNER-01 | xe-0/0/24 (FPC 0) | TBC | 729 |  |

| Link | Path | Ref | Logical Circuit Ref(s) | Service (EWL) | Site A | Site A Floor | Site A Room | Site A Rack | Site B | Site B Floor | Site B Room | Site B Rack |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SW -> LD5 | SW-Leaf to SW-ADVA; LD5-ADVA to LD5-Juniper | 2C06196773 | 2C06196764, 2C06196767 | EWL006955996 | SW | Ground floor | Data Hall 4B | P23 Rack | LD5 | Ground Floor | LD5:0G:00GMC4 | Cabinet:0223, PP:0223:1200068 |
| SW -> LD8 | SW-Leaf to SW-ADVA; LD8-ADVA to LD8-Juniper | 2C06200968 | 2C06200932, 2C06200963 | EWL006956256 | SW | Basement Level 2 | D3 Room | RackSWIB2D3 Location-ISN2 | LD8 | 5th Floor | LD8:05:01MC5C | Cabinet:0404, PP:0404:1339789 |
| UXB -> LD5 | UXB-Leaf to UXB-ADVA; LD5-ADVA to LD5-Juniper | 2C06196170 | 2C06196146, 2C06196166 | EWL006955896 | UXB | Ground floor | Data Hall 4B | P23 Rack | LD5 | Ground Floor | LD5:0G:00GMC4 | Cabinet:0223, PP:0223:1200068 |
| UXB -> LD8 | UXB-Leaf to UXB-ADVA; LD8-ADVA to LD8-Juniper | 2C06197381 | 2C06197378, 2C06197373 | EWL006956033 | UXB | Ground floor | Data Hall 4B | P24 | LD8 | 5th Floor | LD8:05:01MC5C | Cabinet:0404, PP:0404:1339789 |
| LD5 -> LD8 | LD5-Juniper to LD5-ADVA; LD8-ADVA to LD8-Juniper | 2C06214492 | 2C06214474, 2C06214488 | EWL006960897 | LD5 | Ground Floor | LD5:0G:00GMC4 | Cabinet:0223, PP:0223:1200068 | LD8 | 5th Floor | LD8:05:01MC5C | Cabinet:0404, PP:0404:1339789 |

## Flow Topology / Technical Schematic

Figure 1: how the build works.  One eBGP session per link with DENY-ALL, so no routes are exchanged.

Figure 2: physical links and ports.

## Resource requirements

Network engineers to add the configuration and the same to complete patcing activities

# Implementation Summary

## Change Window

- Start Time: 09:00

- End Time: 13:50

- Duration: 4 hours 50 minutes.

(Implementation + validation + rollback if required, excl. hyper care)

## Outage Timings (if any)

- Start Time: n/a

- End Time: n/a

- Duration: no outage

## Execution Summary & Communication Plan

| # | Task Description | Day # | Start (GMT/BST) | End (GMT/BST) | Duration (hh:mm) | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Pre-requisites and pre-checks (section 4.1) | 1 | 09:00 | 11:10 | 02:10 | Jonathan Clowes |
| 2 | Implementation: EX4650 build and commit, steps 1 to 6 | 1 | 11:10 | 11:50 | 00:40 | Jonathan Clowes |
| 3 | Implementation: ACI access policies and MCX_L3OUT, steps 7,8 and 9 | 1 | 11:50 | 12:45 | 00:55 | Jonathan Clowes |
| 4 | Post change validation (section 5) | 1 | 12:45 | 13:20 | 00:35 | Jonathan Clowes |
| 5 | Rollback if required (section 6) | 1 | 13:20 | 13:50 | 00:30 | Jonathan Clowes |
| 6 | Update Helix | 1 | 13:45 | 13:50 | 00:05 | Andrew MacPhail |

Note: Put only day numbers in this plan, actual dates into the Helix Change Record

For more complex changes, complete the following sections, detailing the steps needed to successfully complete this change.

# Detailed Implementation Plan

## Pre-Requisites, Testing & Communication

| # | Task Description | Day # | Start (GMT/BST) | End (GMT/BST) | Duration (hh:mm) | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | EX4650 pre-checks, MCX-LD5-EX4650-INNER-01 and MCX-LD8-EX4650-INNER-01 Confirms the switches are healthy and that everything this change uses is free, so nothing existing is overwritten. Run on both switches in operational mode and save all output to the session log. Virtual chassis healthy show virtual-chassis Expected: 4 members present, master and backup on FPC 0 and FPC 1. No optics in the ports used show chassis hardware ¦ match Xcvr Expected: no transceiver listed in xe-0/0/20 or xe-1/0/20 on either switch until the circuits are patched. Ports free show configuration interfaces ¦ display set ¦ match "xe-[01]/0/2[0-4]" Result LD5: no config on any of the ports. Result LD8: xe-0/0/20 to xe-0/0/24 have unit 0 family ethernet-switching storm-control default, which is removed from xe-0/0/20 and xe-0/0/24 by step 2. xe-1/0/20 to xe-1/0/24 have no config. VLANs 725 to 729 free show configuration vlans ¦ display set ¦ match "vlan-id 72[5-9]" Expected: no match. Result LD5 and LD8: no match. irb.725 to irb.729 free show configuration interfaces irb ¦ display set ¦ match "unit 72[5-9]" Expected: no match. Result LD5 and LD8: no match. New subnets not routed show route table mcx_vrf.inet.0 10.158.240.240/28 show route table mcx_vrf.inet.0 10.157.240.208/28 show route table mcx_vrf.inet.0 <LD5 to LD8 /30> Expected: no exact or more specific match. Result LD5 and LD8: no match for either range. Check local AS used by mcx_vrf show configuration routing-instances mcx_vrf routing-options ¦ display set ¦ match autonomous show configuration routing-options ¦ display set ¦ match autonomous show configuration routing-instances mcx_vrf protocols bgp ¦ display set ¦ match local-as Expected: mcx_vrf uses 64635 on LD5 and 64636 on LD8, and no local-as is set on the existing groups that would change this. BGP baseline show bgp summary Expected: 7 peers Established. Record the prefix counts for comparison after the change. no name clash show configuration policy-options ¦ display set ¦ match DENY-ALL show configuration routing-instances mcx_vrf protocols bgp ¦ display set ¦ match "mcx-aci¦mcx-ld" Expected: no output. If DENY-ALL already exists, check it is the same reject-all policy before reusing it. | 1 | 09:00 | 09:15 | 00:15 | Jonathan Clowes |
| 2 | APIC pre-checks, SWI and UXB Confirms the leaf ports, VLANs and subnets are free on both fabrics. Leaf port Eth1/40 free Fabric > Inventory > leaf 1701 and 1702 on SWI, and leaf 2703 and 2704 on UXB, or from the CLI: fabric 1701,1702 show interface ethernet 1/40 brief fabric 2703,2704 show interface ethernet 1/40 brief Expected: port down with no description or policy. Result SWI: free. Result UXB: not yet confirmed. VLANs not used as an encap moquery -c l3extRsPathL3OutAtt,fvRsPathAtt ¦ grep "^encap" ¦ sort -u Expected: no vlan-725 or vlan-726 on SWI, and no vlan-727 or vlan-728 on UXB. Result SWI and UXB: not in use. The list is long, so paste it into a text editor and search. VLANs not already in a pool Fabric > Access Policies > Pools > VLAN, check the pools used on the border leafs. Expected: 725 to 728 not inside any existing pool range. New subnets not configured anywhere in the fabric moquery -c l3extRsPathL3OutAtt,l3extMember,l3extIp,fvSubnet ¦ egrep "^(addr¦ip) " ¦ grep 10.158 ¦ sort -u On UXB use grep 10.157. Expected: nothing in 10.158.240.240 to .255 on SWI, or 10.157.240.208 to .223 on UXB. | 1 | 09:15 | 09:25 | 00:10 | Jonathan Clowes |
| 3 | APIC and NDO objects the build relies on, SWI and UXB Confirms the existing policies and templates the new objects use, so the right names are used on the night. NDO templates in sync In NDO, check SWI_CONTRACT_L3OUT_TMPLT in PROD_SWI_BD_EPG_APP_L3OUT-SCHM and UXB_CONTRACT_L3OUT-TMPLT in PROD_UXB_BD_EPG_APP_L3OUT-SCHM are In Sync, so deploying them in step 8 only pushes MCX_L3OUT. SWI_PROD_BD_EPG_APP_CONTRACT-TMPLT is currently Out Of Sync. This change does not deploy it, but the reason should be understood and recorded before the change. Expected: both L3Out templates In Sync. Existing BGP timers and BFD policies moquery -c bgpCtxPol ¦ egrep "^name¦^holdIntvl¦^kaIntvl" moquery -c bfdIfPol ¦ egrep "^name¦^minTxIntvl¦^minRxIntvl¦^detectMult" Expected: a BGP timers policy of 10/30 and a BFD interface policy of 300/300/3. Record the names for step 8, and note any that need creating. Router IDs SWI 1701 10.158.255.13, 1702 10.158.255.14, UXB 2703 10.157.255.17, 2704 10.157.255.18, as used by PROD_MIG_L3OUT in PROD_VRF. Fault baseline moquery -c faultInst ¦ grep -c "^code" Expected: record the count on each fabric for comparison after the change. | 1 | 09:25 | 09:35 | 00:10 | Jonathan Clowes |
| 4 | Config backups EX4650, both switches show configuration ¦ save /var/tmp/pre-MCX-ACI-change.conf show configuration ¦ display set ¦ no-more Save the display set output to the session log as well. APIC, both fabrics Admin > Config Rollbacks > Create a snapshot now, description the CRQ number. | 1 | 09:35 | 09:40 | 00:05 | Jonathan Clowes |
| 5 | Fibre Checks at all sites Patch fibres in at LD5 LD8 Swindon Uxbridge | 1 | 09:40 | 11:10 | 01:30 | Ashley Wright, Pat Donlon, Shakeel Rashid, Jonathan Clowes. |

Note: Put only day numbers in this plan, actual dates into Change Record

## Implementation

(Change Window Starts)

| # | Task Description | Day # | Start (GMT/BST) | End (GMT/BST) | Duration (hh:mm) | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | (Mandatory: When change starts update Helix to “Implementation in Progress” or if change does not proceed then in Helix Cancel the change with a suitable reason: “No Longer Required / Resources Not Available / To Be Rescheduled”.) | 1 | 11:10 | 11:01 | 00:01 | Jonathan Clowes |
| 2 | EX4650: default the ports used Removes any existing config from the two ports used on each switch, so they start clean. LD5 has no config on these ports, but LD8 xe-0/0/20 still has storm-control from an earlier build. LD5 EX4650 delete interfaces xe-0/0/20 delete interfaces xe-1/0/20 delete interfaces xe-0/0/24 set interfaces xe-0/0/20 disable set interfaces xe-1/0/20 disable set interfaces xe-0/0/24 disable LD8 EX4650 delete interfaces xe-0/0/20 delete interfaces xe-1/0/20 delete interfaces xe-0/0/24 set interfaces xe-0/0/20 disable set interfaces xe-1/0/20 disable set interfaces xe-0/0/24 disable | 1 | 11:11 | 11:15 | 00:04 | Jonathan Clowes |
| 3 | EX4650: VLANs and irbs in mcx_vrf Creates one VLAN and irb per link and puts the irbs in mcx_vrf. On the ACI links the VLAN must match the encap on the leaf SVI, the EX4650 has the first usable address in the /29 and the leaf has the second. On the LD5 to LD8 link, LD5 has the first address in the /30 and LD8 has the second.. Link; Switch; VLAN; irb; EX4650 address; Far end address. LD5 to SWI; MCX-LD5-EX4650-INNER-01; 725; irb.725; 10.158.240.241/29; 10.158.240.242/29 (1701). LD5 to UXB; MCX-LD5-EX4650-INNER-01; 727; irb.727; 10.157.240.217/29; 10.157.240.218/29 (2703). LD8 to SWI; MCX-LD8-EX4650-INNER-01; 726; irb.726; 10.158.240.249/29; 10.158.240.250/29 (1702). LD8 to UXB; MCX-LD8-EX4650-INNER-01; 728; irb.728; 10.157.240.209/29; 10.157.240.210/29 (2704). LD5 to LD8; both; 729; irb.729; <LD5 address>/30 (LD5); <LD8 address>/30 (LD8). LD5 EX4650: VLAN 725, LD5 to SWI set vlans MCX_ACI_SWI_725 vlan-id 725 set vlans MCX_ACI_SWI_725 l3-interface irb.725 set interfaces irb unit 725 description MCX_ACI_SWI set interfaces irb unit 725 family inet address 10.158.240.241/29 set routing-instances mcx_vrf interface irb.725 LD5 EX4650: VLAN 727, LD5 to UXB set vlans MCX_ACI_UXB_727 vlan-id 727 set vlans MCX_ACI_UXB_727 l3-interface irb.727 set interfaces irb unit 727 description MCX_ACI_UXB set interfaces irb unit 727 family inet address 10.157.240.217/29 set routing-instances mcx_vrf interface irb.727 LD8 EX4650: VLAN 726, LD8 to SWI set vlans MCX_ACI_SWI_726 vlan-id 726 set vlans MCX_ACI_SWI_726 l3-interface irb.726 set interfaces irb unit 726 description MCX_ACI_SWI set interfaces irb unit 726 family inet address 10.158.240.249/29 set routing-instances mcx_vrf interface irb.726 LD8 EX4650: VLAN 728, LD8 to UXB set vlans MCX_ACI_UXB_728 vlan-id 728 set vlans MCX_ACI_UXB_728 l3-interface irb.728 set interfaces irb unit 728 description MCX_ACI_UXB set interfaces irb unit 728 family inet address 10.157.240.209/29 set routing-instances mcx_vrf interface irb.728 LD5 EX4650: VLAN 729, LD5 to LD8 set vlans MCX_LD5_LD8_729 vlan-id 729 set vlans MCX_LD5_LD8_729 l3-interface irb.729 set interfaces irb unit 729 description MCX_LD5_LD8 set interfaces irb unit 729 family inet address <LD5 address>/30 set routing-instances mcx_vrf interface irb.729 LD8 EX4650: VLAN 729, LD8 to LD5 set vlans MCX_LD5_LD8_729 vlan-id 729 set vlans MCX_LD5_LD8_729 l3-interface irb.729 set interfaces irb unit 729 description MCX_LD5_LD8 set interfaces irb unit 729 family inet address <LD8 address>/30 set routing-instances mcx_vrf interface irb.729 | 1 | 11:15 | 11:20 | 00:05 | Jonathan Clowes |
| 4 | EX4650: configure the ports to SWI and UXB Sets a description on each port and makes it a trunk carrying its link VLAN tagged. Each link is a single circuit, so there is no aggregated interface. The SWI link is on FPC 0 and the UXB link on FPC 1, so the loss of one FPC only takes down one fabric link at that site. Link; A end device; A end port; B end device; B end port; VLAN. LD5 to SWI; MCX-LD5-EX4650-INNER-01; xe-0/0/20 (FPC 0); SWI-B2D01U37-LEA-1701; Eth1/40; 725. LD8 to SWI; MCX-LD8-EX4650-INNER-01; xe-0/0/20 (FPC 0); SWI-B2D03U44-LEA-1702; Eth1/40; 726. LD5 to UXB; MCX-LD5-EX4650-INNER-01; xe-1/0/20 (FPC 1); UXB leaf 2703; Eth1/40; 727. LD8 to UXB; MCX-LD8-EX4650-INNER-01; xe-1/0/20 (FPC 1); UXB leaf 2704; Eth1/40; 728. LD5 to LD8; MCX-LD5-EX4650-INNER-01; xe-0/0/24 (FPC 0); MCX-LD8-EX4650-INNER-01; xe-0/0/24 (FPC 0); 729. LD5 EX4650: xe-0/0/20 to SWI leaf 1701 set interfaces xe-0/0/20 description to_SWI-1701-Eth1/40 set interfaces xe-0/0/20 unit 0 family ethernet-switching interface-mode trunk set interfaces xe-0/0/20 unit 0 family ethernet-switching vlan members MCX_ACI_SWI_725 LD5 EX4650: xe-1/0/20 to UXB leaf 2703 set interfaces xe-1/0/20 description to_UXB-2703-Eth1/40 set interfaces xe-1/0/20 unit 0 family ethernet-switching interface-mode trunk set interfaces xe-1/0/20 unit 0 family ethernet-switching vlan members MCX_ACI_UXB_727 LD5 EX4650: <LD5 port> to LD8 set interfaces xe-0/0/24 description to_MCX-LD8-EX4650-INNER-01 set interfaces xe-0/0/24 unit 0 family ethernet-switching interface-mode trunk set interfaces xe-0/0/24 unit 0 family ethernet-switching vlan members MCX_LD5_LD8_729 LD8 EX4650: xe-0/0/20 to SWI leaf 1702 set interfaces xe-0/0/20 description to_SWI-1702-Eth1/40 set interfaces xe-0/0/20 unit 0 family ethernet-switching interface-mode trunk set interfaces xe-0/0/20 unit 0 family ethernet-switching vlan members MCX_ACI_SWI_726 LD8 EX4650: xe-1/0/20 to UXB leaf 2704 set interfaces xe-1/0/20 description to_UXB-2704-Eth1/40 set interfaces xe-1/0/20 unit 0 family ethernet-switching interface-mode trunk set interfaces xe-1/0/20 unit 0 family ethernet-switching vlan members MCX_ACI_UXB_728 LD8 EX4650: <LD8 port> to LD5 set interfaces xe-0/0/24 description to_MCX-LD5-EX4650-INNER-01 set interfaces xe-0/0/24 unit 0 family ethernet-switching interface-mode trunk set interfaces xe-0/0/24 unit 0 family ethernet-switching vlan members MCX_LD5_LD8_729 | 1 | 11:20 | 11:25 | 00:05 | Jonathan Clowes |
| 5 | EX4650: BGP to the SWI and UXB leafs, with deny-all Adds a BGP group in mcx_vrf for each link, including LD5 to LD8, with DENY-ALL in and out so the sessions come up without sending or accepting any routes. Routes are also blocked at the ACI end. MCX_L3OUT has import route control enforcement on with nothing permitted, so nothing from the EX4650 is accepted, and with no BDs associated, no export route control and no default route leak policy, the fabric advertises nothingEvery session uses MD5, BFD at 300 ms x 3 and a hold time of 30. LD5 EX4650: deny-all policy set policy-options policy-statement DENY-ALL term all then reject LD5 EX4650: BGP to SWI leaf 1701 set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers type external set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers peer-as 64631 set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers hold-time 30 set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers neighbor 10.158.240.242 description SWI-1701 set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers authentication-key "<MD5 key>" set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers bfd-liveness-detection minimum-interval 300 set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers bfd-liveness-detection multiplier 3 set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers import DENY-ALL set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers export DENY-ALL LD5 EX4650: BGP to UXB leaf 2703 set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers type external set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers peer-as 64633 set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers hold-time 30 set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers neighbor 10.157.240.218 description UXB-2703 set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers authentication-key "<MD5 key>" set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers bfd-liveness-detection minimum-interval 300 set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers bfd-liveness-detection multiplier 3 set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers import DENY-ALL set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers export DENY-ALL LD5 EX4650: BGP to LD8 set routing-instances mcx_vrf protocols bgp group mcx-ld8-peers type external set routing-instances mcx_vrf protocols bgp group mcx-ld8-peers peer-as 64636 set routing-instances mcx_vrf protocols bgp group mcx-ld8-peers hold-time 30 set routing-instances mcx_vrf protocols bgp group mcx-ld8-peers neighbor <LD8 address> description MCX-LD8 set routing-instances mcx_vrf protocols bgp group mcx-ld8-peers authentication-key "<MD5 key>" set routing-instances mcx_vrf protocols bgp group mcx-ld8-peers bfd-liveness-detection minimum-interval 300 set routing-instances mcx_vrf protocols bgp group mcx-ld8-peers bfd-liveness-detection multiplier 3 set routing-instances mcx_vrf protocols bgp group mcx-ld8-peers import DENY-ALL set routing-instances mcx_vrf protocols bgp group mcx-ld8-peers export DENY-ALL LD8 EX4650: deny-all policy set policy-options policy-statement DENY-ALL term all then reject LD8 EX4650: BGP to SWI leaf 1702 set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers type external set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers peer-as 64631 set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers hold-time 30 set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers neighbor 10.158.240.250 description SWI-1702 set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers authentication-key "<MD5 key>" set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers bfd-liveness-detection minimum-interval 300 set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers bfd-liveness-detection multiplier 3 set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers import DENY-ALL set routing-instances mcx_vrf protocols bgp group mcx-aci-swi-peers export DENY-ALL LD8 EX4650: BGP to UXB leaf 2704 set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers type external set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers peer-as 64633 set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers hold-time 30 set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers neighbor 10.157.240.210 description UXB-2704 set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers authentication-key "<MD5 key>" set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers bfd-liveness-detection minimum-interval 300 set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers bfd-liveness-detection multiplier 3 set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers import DENY-ALL set routing-instances mcx_vrf protocols bgp group mcx-aci-uxb-peers export DENY-ALL LD8 EX4650: BGP to LD5 set routing-instances mcx_vrf protocols bgp group mcx-ld5-peers type external set routing-instances mcx_vrf protocols bgp group mcx-ld5-peers peer-as 64635 set routing-instances mcx_vrf protocols bgp group mcx-ld5-peers hold-time 30 set routing-instances mcx_vrf protocols bgp group mcx-ld5-peers neighbor <LD5 address> description MCX-LD5 set routing-instances mcx_vrf protocols bgp group mcx-ld5-peers authentication-key "<MD5 key>" set routing-instances mcx_vrf protocols bgp group mcx-ld5-peers bfd-liveness-detection minimum-interval 300 set routing-instances mcx_vrf protocols bgp group mcx-ld5-peers bfd-liveness-detection multiplier 3 set routing-instances mcx_vrf protocols bgp group mcx-ld5-peers import DENY-ALL set routing-instances mcx_vrf protocols bgp group mcx-ld5-peers export DENY-ALL | 1 | 11:25 | 11:35 | 00:10 | Jonathan Clowes |
| 6 | EX4650: review and commit Checks the staged config from steps 2 to 5 and applies it. commit confirmed rolls the switch back automatically after 5 minutes unless the commit is confirmed, so a mistake that cuts off access or drops the existing peers undoes itself. Do LD5 first, then LD8. show ¦ compare commit check commit confirmed 5 In show ¦ compare, only the three ports, VLANs, irbs, BGP groups and the DENY-ALL policy should appear, and the only deletion should be the old storm-control config on LD8. Commit needs to be doen witing 5 minutes Run show bgp summary commit | 1 | 11:35 | 11:50 | 00:15 | Jonathan Clowes |
| 7 | ACI: access policies, SWI and UXB Builds the access policies for Eth1/40 on each leaf, in order, as each object points at the one before: VLAN pool, L3 domain, AEP, access port policy group and port assignment. Existing objects are not touched. SWI APIC: VLAN pool Fabric > Access Policies > Pools > VLAN. Name SWI_L3OUT_MCX_VLP, allocation mode Static, encap block 725-726, allocation mode Inherit, role External. SWI APIC: L3 domain Physical and External Domains > L3 Domains. Name SWI_MCX_L3OUT_DOM, VLAN pool SWI_L3OUT_MCX_VLP. SWI APIC: AEP Policies > Global > Attachable Access Entity Profiles. Name SWI_MCX_AEP, domain SWI_MCX_L3OUT_DOM. SWI APIC: leaf access port policy group Interfaces > Leaf Interfaces > Policy Groups > Leaf Access Port. Name SWI_MCX_ACC_IPG, link level policy 10G, LLDP enabled, AEP SWI_MCX_AEP. SWI APIC: port assignment Interface Configuration > Actions > Configure Interfaces. Node type Leaf, port type Access, interface type Ethernet, interface aggregation type Individual. Node 1701 interface 1/40, policy group SWI_MCX_ACC_IPG, description to_MCX-LD5-EX4650-INNER-01. Node 1702 interface 1/40, policy group SWI_MCX_ACC_IPG, description to_MCX-LD8-EX4650-INNER-01. UXB APIC: VLAN pool Fabric > Access Policies > Pools > VLAN. Name UXB_L3OUT_MCX_VLP, allocation mode Static, encap block 727-728, allocation mode Inherit, role External. UXB APIC: L3 domain Physical and External Domains > L3 Domains. Name UXB_MCX_L3OUT_DOM, VLAN pool UXB_L3OUT_MCX_VLP. UXB APIC: AEP Policies > Global > Attachable Access Entity Profiles. Name UXB_MCX_AEP, domain UXB_MCX_L3OUT_DOM. UXB APIC: leaf access port policy group Interfaces > Leaf Interfaces > Policy Groups > Leaf Access Port. Name UXB_MCX_ACC_IPG, link level policy 10G, LLDP enabled, AEP UXB_MCX_AEP. UXB APIC: port assignment Interface Configuration > Actions > Configure Interfaces. Node type Leaf, port type Access, interface type Ethernet, interface aggregation type Individual. Node 2703 interface 1/40, policy group UXB_MCX_ACC_IPG, description to_MCX-LD5-EX4650-INNER-01. Node 2704 interface 1/40, policy group UXB_MCX_ACC_IPG, description to_MCX-LD8-EX4650-INNER-01. Check on each fabric that the Interface Configuration table lists Eth1/40 on each leaf with the right policy group and no faults. Until the circuits are connected the ports will be down, which is expected. | 1 | 11:50 | 12:05 | 00:15 | Jonathan Clowes |
| 8 | ACI: MCX_L3OUT in PROD, SWI and UXB Creates one L3Out per fabric for the LD5 and LD8 links. As with our other L3Outs, the L3Out and external EPG are created in NDO and the node profile, interface profiles and BGP peers are added on the APIC. Each link lands on one leaf, so each leaf has one SVI and one BGP peer. The router IDs match those already used in PROD_VRF for PROD_MIG_L3OUT, as ACI needs a node to use the same router ID across all its L3Outs in a VRF, and MTU is set to 1500 to match the EX4650. Route control enforcement is set for import and export, so the L3Out only accepts or sends routes that are explicitly allowed. Nothing is allowed yet, so no routes are exchanged. SWI: L3Out and external EPG, in NDO 1. In NDO go to Manage > Tenant Templates > Application, open schema PROD_SWI_BD_EPG_APP_L3OUT-SCHM and select template SWI_CONTRACT_L3OUT_TMPLT. 2. Click Create Object > L3Out, name it MCX_L3OUT and set the VRF to the existing PROD_VRF. 3. On the SWINDON tab, select MCX_L3OUT and set the L3 domain to SWI_MCX_L3OUT_DOM. 4. Click Create Object > External EPG, name it MCX_L3OUT_EXT_EPG, set the L3Out to MCX_L3OUT and leave it with no subnets. 5. Save the schema and deploy this template only. 6. On the SWI APIC, open Tenants > PROD_TNT > Networking > L3Outs > MCX_L3OUT and check it is there with VRF PROD_VRF and domain SWI_MCX_L3OUT_DOM. 7. On the L3Out Policy tab, tick BGP and tick Route Control Enforcement Import, leaving Export ticked, then Submit. SWI: node profile, on the APIC 1. Under MCX_L3OUT, right-click Logical Node Profiles > Create Node Profile and name it MCX_NODE_PROF. 2. Add node 1701 with router ID 10.158.255.13 and untick Use Router ID as Loopback Address. 3. Add node 1702 with router ID 10.158.255.14 and untick Use Router ID as Loopback Address. 4. Under MCX_NODE_PROF, create a BGP Protocol Profile and select the 10/30 BGP timers policy recorded in the pre-checks, then Submit. SWI: interface profile for LD5, on the APIC 1. Under MCX_NODE_PROF, right-click Logical Interface Profiles > Create Interface Profile and name it MCX_LD5_IFP. 2. Create a BFD Interface Profile on it and select the 300/300/3 BFD policy recorded in the pre-checks. 3. On the SVI tab, add a path: path type Port, node 1701, path eth1/40, encap VLAN 725, mode Trunk, IP address 10.158.240.242/29, MTU 1500. 4. Under that path, create a BGP Peer Connectivity Profile: peer address 10.158.240.241, remote AS 64635, the MD5 password, and tick BFD under Peer Controls. Leave local AS blank. 5. Submit. SWI: interface profile for LD8, on the APIC 1. Under MCX_NODE_PROF, right-click Logical Interface Profiles > Create Interface Profile and name it MCX_LD8_IFP. 2. Create a BFD Interface Profile on it and select the 300/300/3 BFD policy recorded in the pre-checks. 3. On the SVI tab, add a path: path type Port, node 1702, path eth1/40, encap VLAN 726, mode Trunk, IP address 10.158.240.250/29, MTU 1500. 4. Under that path, create a BGP Peer Connectivity Profile: peer address 10.158.240.249, remote AS 64636, the MD5 password, and tick BFD under Peer Controls. Leave local AS blank. 5. Submit. UXB: L3Out and external EPG, in NDO 1. In NDO go to Manage > Tenant Templates > Application, open schema PROD_UXB_BD_EPG_APP_L3OUT-SCHM and select template UXB_CONTRACT_L3OUT-TMPLT. 2. Click Create Object > L3Out, name it MCX_L3OUT and set the VRF to the existing PROD_VRF. 3. On the UXBRIDGE tab, select MCX_L3OUT and set the L3 domain to UXB_MCX_L3OUT_DOM. 4. Click Create Object > External EPG, name it MCX_L3OUT_EXT_EPG, set the L3Out to MCX_L3OUT and leave it with no subnets. 5. Save the schema and deploy this template only. 6. On the UXB APIC, open Tenants > PROD_TNT > Networking > L3Outs > MCX_L3OUT and check it is there with VRF PROD_VRF and domain UXB_MCX_L3OUT_DOM. 7. On the L3Out Policy tab, tick BGP and tick Route Control Enforcement Import, leaving Export ticked, then Submit. UXB: node profile, on the APIC 1. Under MCX_L3OUT, right-click Logical Node Profiles > Create Node Profile and name it MCX_NODE_PROF. 2. Add node 2703 with router ID 10.157.255.17 and untick Use Router ID as Loopback Address. 3. Add node 2704 with router ID 10.157.255.18 and untick Use Router ID as Loopback Address. 4. Under MCX_NODE_PROF, create a BGP Protocol Profile and select the 10/30 BGP timers policy recorded in the pre-checks, then Submit. UXB: interface profile for LD5, on the APIC 1. Under MCX_NODE_PROF, right-click Logical Interface Profiles > Create Interface Profile and name it MCX_LD5_IFP. 2. Create a BFD Interface Profile on it and select the 300/300/3 BFD policy recorded in the pre-checks. 3. On the SVI tab, add a path: path type Port, node 2703, path eth1/40, encap VLAN 727, mode Trunk, IP address 10.157.240.218/29, MTU 1500. 4. Under that path, create a BGP Peer Connectivity Profile: peer address 10.157.240.217, remote AS 64635, the MD5 password, and tick BFD under Peer Controls. Leave local AS blank. 5. Submit. UXB: interface profile for LD8, on the APIC 1. Under MCX_NODE_PROF, right-click Logical Interface Profiles > Create Interface Profile and name it MCX_LD8_IFP. 2. Create a BFD Interface Profile on it and select the 300/300/3 BFD policy recorded in the pre-checks. 3. On the SVI tab, add a path: path type Port, node 2704, path eth1/40, encap VLAN 728, mode Trunk, IP address 10.157.240.210/29, MTU 1500. 4. Under that path, create a BGP Peer Connectivity Profile: peer address 10.157.240.209, remote AS 64636, the MD5 password, and tick BFD under Peer Controls. Leave local AS blank. 5. Submit. Check there are no faults on MCX_L3OUT on either fabric, in particular no router ID or encap faults. | 1 | 12:05 | 12:40 | 00:35 | Jonathan Clowes |
| 9 | Enable the interfaces for all five circuits LD5 EX4650 delete interfaces xe-0/0/20 delete interfaces xe-1/0/20 delete interfaces xe-0/0/24 set interfaces xe-0/0/20 disable set interfaces xe-1/0/20 disable set interfaces xe-0/0/24 disable LD8 EX4650 delete interfaces xe-0/0/20 delete interfaces xe-1/0/20 delete interfaces xe-0/0/24 set interfaces xe-0/0/20 disable set interfaces xe-1/0/20 disable set interfaces xe-0/0/24 disable | 1 | 12:40 | 12:45 | 0:05 | Jonathon Clowes |

Note: Put only day numbers in this plan, actual dates into the Helix Change Record

# Post Change Validation Testing

Confirmation (does not include hyper care)

| # | Task Description | Day # | Start (GMT/BST) | End (GMT/BST) | Duration (hh:mm) | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Fabric links up Both EX4650s show interfaces terse xe-0/0/20 show interfaces terse xe-1/0/20 show interfaces diagnostics optics xe-0/0/20 show interfaces terse xe-0/0/24 SWI and UXB APIC fabric 1701,1702 show interface ethernet 1/40 brief fabric 2703,2704 show interface ethernet 1/40 brief Expected: all four fabric links up at both ends, with receive light within the optic's range. | 1 | 12:45 | 12:50 | 00:05 | Jonathan Clowes |
| 2 | IP reachability LD5 EX4650 ping 10.158.240.242 routing-instance mcx_vrf count 5 ping 10.157.240.218 routing-instance mcx_vrf count 5 ping <LD8 address> routing-instance mcx_vrf count 5 LD8 EX4650 ping 10.158.240.250 routing-instance mcx_vrf count 5 ping 10.157.240.210 routing-instance mcx_vrf count 5 ping <LD5 address> routing-instance mcx_vrf count 5 Expected: all reply. | 1 | 12:50 | 12:55 | 00:05 | Jonathan Clowes |
| 3 | BFD and BGP established with no prefixes Both EX4650s show bfd session show bgp summary SWI and UXB APIC fabric 1701,1702 show bgp ipv4 unicast summary vrf PROD_TNT:PROD_VRF fabric 2703,2704 show bgp ipv4 unicast summary vrf PROD_TNT:PROD_VRF Expected: BFD up and BGP Established on the SWI and UXB sessions, two per EX4650 and one per leaf, with 0 received and 0 accepted. | 1 | 12:55 | 13:00 | 00:05 | Jonathan Clowes |
| 4 | No routes exchanged LD5 EX4650, repeat for 10.157.240.218 show route advertising-protocol bgp 10.158.240.242 table mcx_vrf show route receive-protocol bgp 10.158.240.242 table mcx_vrf show route advertising-protocol bgp <LD8 address> table mcx_vrf show route receive-protocol bgp <LD8 address> table mcx_vrf LD8 EX4650, repeat for 10.157.240.210 show route advertising-protocol bgp 10.158.240.250 table mcx_vrf show route receive-protocol bgp 10.158.240.250 table mcx_vrf show route advertising-protocol bgp <LD5 address> table mcx_vrf show route receive-protocol bgp <LD5 address> table mcx_vrf SWI and UXB APIC fabric 1701 show bgp ipv4 unicast neighbors 10.158.240.241 advertised-routes vrf PROD_TNT:PROD_VRF fabric 1702 show bgp ipv4 unicast neighbors 10.158.240.249 advertised-routes vrf PROD_TNT:PROD_VRF fabric 2703 show bgp ipv4 unicast neighbors 10.157.240.217 advertised-routes vrf PROD_TNT:PROD_VRF fabric 2704 show bgp ipv4 unicast neighbors 10.157.240.209 advertised-routes vrf PROD_TNT:PROD_VRF Expected: no routes in either direction on the EX4650s, and no routes advertised by any leaf. | 1 | 13:00 | 13:05 | 00:05 | Jonathan Clowes |
| 5 | Link subnets not advertised north Both EX4650s, for each existing VDOM peer show route advertising-protocol bgp <VDOM peer> table mcx_vrf ¦ match "10.158.240.2¦10.157.240.2" Expected: no output. | 1 | 13:05 | 13:10 | 00:05 | Jonathan Clowes |
| 6 | Nothing else changed Both EX4650s show bgp summary SWI and UXB APIC moquery -c faultInst ¦ grep -c "^code" Expected: the 7 existing peers still Established with the same prefix counts as the pre-check, and no new faults compared with the baseline. | 1 | 13:10 | 13:15 | 00:05 | Jonathan Clowes |
| 7 | NDO in sync NDO in sync In NDO, open SWI_CONTRACT_L3OUT_TMPLT in PROD_SWI_BD_EPG_APP_L3OUT-SCHM and UXB_CONTRACT_L3OUT-TMPLT in PROD_UXB_BD_EPG_APP_L3OUT-SCHM. Expected: both templates In Sync with MCX_L3OUT and MCX_L3OUT_EXT_EPG listed, and no drift reported. | 1 | 13:15 | 13:20 | 00:05 | Jonathan Clowes |
|  | Mandatory: If Implementation has been validated successfully then update status of the Change in Helix to “Completed” – otherwise move on to Rollback | 1 | 13:20 | 13:20 | 00:00 | Andrew MacPhail |

Note: Put only day numbers in this plan, actual dates into the Helix Change Record

Note: Put only day numbers in this plan, actual dates into the Helix Change Record

# Rollback

Complete Back-out and restore to previously good configuration (Change Window ends)

| # | Task Description | Day # | Start (GMT/BST) | End (GMT/BST) | Duration (hh:mm) | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Roll back the EX4650s Removes everything this change added on both switches and leaves the existing config untouched. If nothing else has been committed since the change, use rollback 2. Otherwise load the archive taken in the pre-checks. Do LD8 then LD5. If nothing else has been committed since configure rollback 2 show ¦ compare commit Otherwise configure load override /var/tmp/pre-MCX-ACI-change.conf show ¦ compare commit Expected: show ¦ compare shows only the new config being removed, and the 7 existing peers stay Established. | 1 | 13:20 | 13:30 | 00:10 | Jonathan Clowes |
| 2 | Remove MCX_L3OUT, SWI and UXB Deletes the new L3Out, which removes the SVIs and BGP peers on the leafs. Remove the node and interface profiles on the APIC, then delete MCX_L3OUT and the external EPG from SWI_CONTRACT_L3OUT_TMPLT and UXB_CONTRACT_L3OUT-TMPLT in NDO and redeploy each template, so that NDO and the APIC stay in sync. Expected: no MCX_L3OUT under PROD_TNT on either fabric and no new faults. | 1 | 13:30 | 13:40 | 00:10 | Jonathan Clowes |
| 3 | Remove the ACI access policies, SWI and UXB Deletes the new access policies in the reverse order they were built, so no object is left pointing at one that no longer exists: the port assignments under Interface Configuration, then the access port policy group, the AEP, the L3 domain and the VLAN pool. Expected: Eth1/40 on each leaf shows no policy group and the fault count is back to the baseline. | 1 | 13:40 | 13:45 | 00:05 | Jonathan Clowes |
| 4 | Confirm back to baseline Use the APIC snapshot only as a last resort, because restoring it rolls back the whole fabric config and not just this change. show bgp summary Expected: the 7 existing peers Established with the same prefix counts as the pre-check. | 1 | 13:45 | 13:50 | 00:05 | Jonathan Clowes |
|  | Mandatory: If validation failed and the change was rolled back, then update status of the Change in Helix to “Completed” | 1 | 13:50 | 13:50 | 00:00 | Andrew MacPhail |

Note: Put only day numbers in this plan, actual dates into the Helix Change Record

# Close Down

Within 7 days of Change Completing, you must update Helix and Close the change with the correct status:

| # | Task Description | Owner |
| --- | --- | --- |
| A | Successful—The change request is closed because the request is successful. | Change Coordinator |
| B | Successful with Issues—The change request is closed because the request is successful, but with issues. | Change Coordinator |
| C | Unsuccessful—The change request is closed because the request is unsuccessful. | Change Coordinator |
| D | Backed Out—The change request is closed because the request is backed out. | Change Coordinator |
| E | Auto Closed – The change was auto closed by the system because the coordinator did not update their change within 7 days of completion, success will be reported as Unknown | Helix (Hannah Admin) Automation |